## V2
| Blackboard Group 33 Class NCC | Project Planning Nov. 24 |  |  |  |  | Version 1 Nov. 26 |  |  |  |  | Version 2 Dec. 1 |  |  |  |  | Version 3 Dec. 3 |  |  |  |  | Last Chance Submission
| SMART goals ==> name | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
1 | Group | Meeting #1 for Project Planning (In-person) | Roles and responsibilities assigned. All roles assigned clearly to each member. | (30mins) | 2024-11-13 | DONE
2 | Ashley | Start Draft Project Plan (Excel) | Initial draft plan created. Document reviewed and accepted by the group. | (15mins) | 2024-11-13 | DONE
3 | Vadeeha | Agenda for Meeting #1 (Word Document) | Agenda for Meeting #1 prepared. Agenda shared and acknowledged by the group. | (15mins) | 2024-11-13 | DONE
4 | Michaela | Minutes for Meeting #1 (Word Document) | Minutes of Meeting #1. Minutes are shared and approved by the group. | (30mins) | 2024-11-13 | DONE
5 | Group | Meeting #2 Finalization (In-person) | Revision of roles and responsibilities. New roles and tasks assigned due to Ashley's departure. | 1hr | 2024-11-21 | DONE
6 | Michaela & Vadeeha | Finalize Draft Project Plan (Excel) | Completed project plan draft. Document reviewed and finalized. | (30mins) | 2024-11-21 | DONE
7 | Vadeeha | Agenda for Meeting #2 (Word Document) | Agenda for Meeting #2 prepared. Agenda prepared and shared with group member before meeting. | (10mins) | 2024-11-21 | DONE
8 | Michaela | Minutes for Meeting #2 (Word Document) | Minutes of Meeting #2. Minutes shared with group member for review and accuracy. | (40mins) | 2024-11-21 | DONE
9 | Michaela & Vadeeha | Finalize Project Plan and Check Minutes (Excel & Word Document) | Finalized project plan and reviewed minutes. Both documents are finalized and accurate. | (30mins) | 2024-11-23 | DONE
10 | Michaela & Vadeeha | Approval | Project approved by both members. Both members provided formal confirmation. | (10mins) | 2024-11-23 | DONE
11 | Michaela | Submission for the group (BlackBoard) | Submit the final project plan. All documents are compiled and submitted on time. |  | 2024-11-24 | DONE
12 | Michaela & Vadeeha | Start Filling up Project Plan for V#1 (Excel) | Drafted content for V#1 tasks. Project plan sections for V#1 are started. | TBD | Start 23-Nov | DOING
13 | Michaela | [5 empty] | Create a folder for Version 1 (Group33_FinalProject_V1) | Folder is reviewed, and all necessary files for V#1 are in place. | (15mins) | 2024-11-25 | DONE
14 | Group | [5 empty] | Continued Project Plan for V#1 (Excel) | Initial draft plan created for V#1. Document reviewed and accepted by both member. | (30mins) | 2024-11-25 | DOING
15 | Michaela | [5 empty] | Extract Project Source Code.zip into the folder and open .c files using Visual Studio Code | Files extracted and PNG codes are ready to be transferred to Visual Studio. | (5mins) | 2024-11-25 | DONE
16 | Group | [5 empty] | Meeting #1 for V#1 (In-person) | Meeting held and discussed tasks. Did the transfer code and started commeting on the code while on meeting. | 3hours | 2024-11-25 | DONE
17 | Vadeeha | [5 empty] | Agenda for Meeting #1 for V#1 (Word Document) | Agenda created and reviewed by both members. | (15mins) | 2024-11-25 | DONE
18 | Michaela | [5 empty] | Minutes for Meeting #1 for V#1 (Word Document) | Meeting minutes documented and reviewed by both members. | (40mins) | 2024-11-25 | DONE
19 | Michaela | [5 empty] | Transfer code for fundamentals.c and fundamentals.h | Code transferred successfully, verified by both members. | (30mins) | 2024-11-25 | DONE
20 | Vadeeha | [5 empty] | Transfer code for manipulating.c and manipulating.h | Code transferred successfully, verified by both members. | (30mins) | 2024-11-25 | DONE
21 | Michaela | [5 empty] | Transfer code for tokenizing.c, tokenizing.h and converting.c, converting.h | Code transferred successfully, verified by both members. | (30mins) | 2024-11-25 | DONE
22 | Vadeeha | [5 empty] | Organize and verify code for tokenizing.c, tokenizing.h and converting.c, converting.h | Organized and verified code. Ready for testing phase. | (20mins) | 2024-11-25 | DONE
23 | Group | [5 empty] | Make the main() and add each function/module one by one to check if it's working. Follow the PNG given. | Functions/modules added one by one, verified for correct behavior. | (20mins) | 2024-11-25 | DONE
24 | Vadeeha | [5 empty] | Begin adding comments to each module's code | Code annotated with comments for clarity. | (40mins) | 2024-11-25 | DONE
25 | Michaela | [5 empty] | Run Microsoft cl compiler with the access through Visual Studio IDE | Code compiled successfully without errors. | (10mins) | 2024-11-26 | DONE
26 | Michaela | [5 empty] | Start doing the Test Cases for Fundamentals | Initial test cases written and executed. | (20mins) | 2024-11-26 | DONE
27 | Michaela | [5 empty] | Start doing the Test Cases for Manipulating | Initial test cases written and executed. | (20mins) | 2024-11-26 | DONE
28 | Michaela | [5 empty] | Start doing the Test Cases for Tokenizing | Initial test cases written and executed. | (20mins) | 2024-11-26 | DONE
29 | Michaela | [5 empty] | Start doing the Test Cases for Converting | Initial test cases written and executed. | (20mins) | 2024-11-26 | DONE
30 | Michaela | [5 empty] | Start doing the Test Cases for Main | Initial test cases written and executed. | (20mins) | 2024-11-26
31 | Group | [5 empty] | Meeting #2 for V#1 (In-person) | Continue to discuss tasks, updates reviewed, and next steps planned. | 3hours | 2024-11-26 | DONE
32 | Vadeeha | [5 empty] | Agenda for Meeting #2 for V#1 (Word Document) | Agenda created and reviewed by both members. | (15mins) | 2024-11-26 | DONE
33 | Vadeeha | [5 empty] | Minutes for Meeting #2 for V#1(Word Document) | Meeting minutes documented and reviewed by both members. | (30mins) | 2024-11-26 | DONE
34 | Michaela | [5 empty] | Put the testing output for each module in .txt file | Outputs saved in .txt file, verified by both members for clarity and completeness. | 1 hour | 2024-11-26 | DONE
35 | Group | [5 empty] | Final check of all files for submission | Verified files are ready for submission | (10mins) | 2024-11-26 | DONE
36 | Michaela | [5 empty] | Submit the project on Blackboard | Project submitted successfully on Blackboard. |  | 2024-11-26 | DONE
37 | Vadeeha | [5 empty] | Combine .txt testing files into one document (Word Document) | All .txt files merged and verified for consistency. | (10mins) | 2024-11-27 | DONE
38 | Michaela | [5 empty] | Resubmit, if required (Correct and reupload files) | Files reviewed, corrections applied, and resubmitted if necessary. |  | 2024-11-27 | DONE
39 | Group | [10 empty] | Meeting #1 for V#2 (In-person) | Meeting held and initial tasks for Version 2. | 2024-11-27 | 1 hour | DONE
40 | Michaela | [10 empty] | Agenda for Meeting #1 for V#2 (Word Document) | Agenda documented and approved by both members. | 2024-11-27 | (10mins) | DONE
41 | Michaela | [10 empty] | Minutes for Meeting #1 for V#2 (Word Document) | Minutes completed and reviewed by group. | 2024-11-27 | (40mins) | DONE
42 | Group | [10 empty] | Make a quick and temporary checklist for V#2 | Checklist reviewed and approved for progress. | 2024-11-27 | (15mins) | DONE
43 | Michaela | [10 empty] | Make a git repository | Repository created. | 2024-11-27 | (15mins) | DONE
44 | Group | [10 empty] | Meeting #2 for V#2 (In-person) | Discussed progress and prepared tasks for submission. | 2024-11-29 | 3 hours | DONE
45 | Vadeeha | [10 empty] | Agenda for Meeting #2 for V#2 (Word Document) | Agenda documented and approved by both members. | 2024-11-29 | (15mins) | DONE
46 | Vadeeha | [10 empty] | Minutes for Meeting #2 for V#2 (Word Document) | Minutes completed and reviewed by group. | 2024-11-29 | (40mins) | DONE
47 | Vadeeha | [10 empty] | Add comments to all the modules for V#2 | Comments added and verified for correctness. | 2024-11-29 | 1 hour | DONE
48 | Michaela | [10 empty] | Start doing the Test Cases for Fundamentals | Test cases created, executed, and documented. | 2024-11-29 | (35mins) | DONE
49 | Vadeeha | [10 empty] | Start doing the Test Cases for Manipulating | Test cases created, executed, and documented. | 2024-11-29 | (35mins) | DONE (by Michaela)
50 | Michaela & Vadeeha | [10 empty] | Start doing the Test Cases for Tokenizing | Test cases created, executed, and documented. | 2024-11-29 | (35mins) | DONE (by Michaela)
51 | Michaela & Vadeeha | [10 empty] | Start doing the Test Cases for Converting | Test cases created, executed, and documented. | 2024-11-29 | (35mins) | DONE (by Michaela)
52 | Michaela | [10 empty] | Update git | Git repository updated with Version 1 files. | 2024-11-30 | (40mins) | DONE
53 | Michaela | [10 empty] | Combine the test cases (Word Document) | Combined all test case files into a single document. | 2024-11-30 | (35mins) | DONE
54 | Michaela & Vadeeha | [10 empty] | Finalize and verify files for V#2 | Final review of all the files, ensuring all details are accurate. | 2024-11-30 | (30mins) | DONE
55 | Michaela | [10 empty] | Verify git upload for V#2 | Checked repository for completeness and file integrity. | 2024-11-30 | (40mins) | DOING
56 | Michaela | [10 empty] | Submission for V#2 | Submit all deliverables for Version 2 on Blackboard. | 2024-12-01 |  | DOING
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
Note on B1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on B2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on C2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on D2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on E2: How many hours will the task take?
Note on F2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on G2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on H2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on I2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on J2: How many hours will the task take?
Note on K2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on L2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on M2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on N2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on O2: How many hours will the task take?
Note on P2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Q2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on R2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on S2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on T2: How many hours will the task take?
Note on U2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on V2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on W2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on X2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on Y2: How many hours will the task take?
Note on Z2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on AA2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.